## Slide 1: Governance Sub Themes: (HRMIS, M&E, Biometrics, Communication Strengthening, School Consolidation)
By: Mr. Akram Khowaja
Director General Monitoring & Evaluation- E&LD
Education & Literacy Department
Government of Sindh
JESR-II

## Slide 2: Disclaimer: This presentation is solely for the purpose of reference and not intended for wider dissemination and preferably to be circulated only within Local Education Group (LEG) Members and the participants of the JESR-II event. The material in this presentation has been compiled from different sources and for any further clarity, kindly contact Reform Support Unit, Education & Literacy Deptt, Govt of Sindh.
Education & Literacy Department
Government of Sindh
JESR-II

## Slide 3
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Status | Implementation Challenges | Timelines
1. | Develop Sindh Education Policy | First set of deliberations held and steps taken for notifying Task Force for the development of Sindh Education Policy. | This being the first Provincial Education Policy post 18th amendment, there would be challenges in evolving a Policy that adequately identifies and responds to the needs and is based on a broad based consultation/consensus. | 6 months
2. | Introduce and establish a robust, independent, Monitoring & Evaluation System at E&LD | Conceptual and implementation framework for M&E developed and agreed; Positions of 15 districts sanctioned and 225 Monitoring Assistants & Chief Monitoring Officers recruited; M&E Directorate General established at Karachi along with 15 district offices; Biometric registration (teaching and non-teaching). |  | 
SESP JESR II : Governance & Accountability

## Slide 4
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Status | Implementation Challenges | Timelines
 |  | IT equipment including smartphones and biometric devices procured and provided to the MAs, along with facility for mobility; System of data collection established and data being collected from the 15 districts, with almost 100% coverage / outreach achieved. As a regular feature, data is being uploaded on server and summary made available on the dashboard; Monitoring process notified and training manual prepared; Monthly reports now being produced and made available, since the last 4 months. Positions of remaining 14 districts requested from the Finance Department and staff recruitment and procurement processes initiated for completing the roll out. | Budget (salary and non-salary) approval for the remaining 14 districts of Sindh; Staff recruitment and establishing M&E offices in the remaining 14 districts. | 3 months
SESP JESR II : Governance & Accountability

## Slide 5
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Status | Implementation Challenges | Timelines
3. | Establish Management Cadre | Management Cadre and the Service Rules framed / notified on 23rd July 2014; Appropriations for the posts made in the budgets for FY 2014-15 and appointments made; For FY 2016-17, district-wise budget appropriations sought from the Finance Department; Implementation partial/ full implementation subject to the final decision of the Services Tribunal & the Supreme Court. | Supreme Court’s decision will be binding and would unfold the details of permissible aspects of education management policy implementation. | No timelines can be given as the matter is prejudice.
4. | Establish Human Resources Management Information System | System Analysis, full scale HRMIS development, data entry and warehousing already completed; Sync files made on monthly basis from 3 data sources for verification / data purification (AG, Biometric and SEMIS); Discrepancies being filtered on a regular basis. | Since the HRMIS data is sensitive, another real challenge is to achieve high level of reliability, accuracy & authenticity. | 9 months (this may take some more time as the obj. is to achieve 100% accuracy)
SESP JESR II : Governance & Accountability

## Slide 6
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Status | Implementation Challenges | Timelines
5. | Establish Internal Audit System | First ever Internal Audit Charter of Sindh, developed. with support of EU, approved by CM / notified by GoS. First ever, Internal Audit Law and rules drafted and endorsed by GoS Committee and moved for approvals / legislation; Draft Organizational structure developed and agreed. FD has approved in principle, all positions. Summary for creating positions within September. | The process of sanctioning positions and legislation can be time consuming, however the Finance Department is making the effort. | 9 months
6. | Cluster-based School Management System | With the support of EU, Clustering Policy framed and notified / SOPs approved; 62 Clusters formed in 6 pilot districts where orientation was given 380 HMs / Others. | Since this is a major policy reform, it would need continuous support and patronage by all concerned. | 9 months
SESP JESR II: Governance & Accountability

## Slide 7
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Status | Implementation Challenges | Timelines
7. | Professional Development/Capacity building of DDOs and Procuring Officials | Training made mandatory at all management levels by GoS (eligibility for promotion); Various programs for improving the capacity of finance/DDOs and procuring officials of GoS held in all districts, with the support of the WB, EU, others for school consolidation etc. Other programs designed along with SPPRA. | Sustainable approach and institutional arrangements to be ensured. | 9 months
8. | Better equipped Offices and Logistics | Initial deliberations held internally and with EU (added as a policy trigger) First steps undertaken to assess needs in terms of offices, transport and budget requirements. | This would require additional funding / approval for purchase of vehicles. | 9 months
SESP JESR II : Governance & Accountability

## Slide 8
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Status | Implementation Challenges | Timelines
9. | Establish New System of Performance Appraisal | Agreed by GoS as policy reform area and even included as a policy trigger with EU TA. | Real challenge would be in the implementation of the system. | 9-12 months
10. | Establish Information and Communication Unit | A fully functional Communications Unit established; Communications Strategy being finalized; Robust SMS-based complaint management system (ILMI) established & effectively managed by E&LD; Regular position of Communication Specialist appropriated in the budget; Publications on key reforms are being regularly issued by E&LD; E&LD Website improved and made more interactive, current and informative. | Sustainability is key to ensuring effective communication and that the outputs / outcomes are utilized in decision making. | ICS Pilot launch tentatively by October’16 with full launch in Feb’17.
SESP JESR II : Governance & Accountability

## Slide 9
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Status | Implementation Challenges | Timelines
11. | Increase effectiveness of SMCs | SMC funding formula has been revised; Standard Operating Procedures (SOPs) developed for effective and easy banking operations of SMC Accounts; New SOPs have been approved by the competent authority, to receive SMC grants; Devised eligibility criteria for SMC’s release of funds. | Delayed response from the districts. Funds Utilization / Tracking. Community involvement | 9 months
12. | Establish R&D Unit | Unit notified in July, 2016. Office established at E&LD under PDR Two personnel of SCDP already deputed there Series of trainings planned to be conducted shortly. 18 Officers already nominated | Appropriate personnel for placement Budget allocation in the CFY as no appropriation is there | 6 months
SESP JESR II : Governance & Accountability

## Slide 10
Education & Literacy Department
Government of Sindh
JESR-II
Name of Districts | District Group Members | Observation
Karachi | Mr. Siraj Ahmed Chandio Monitoring Assistant M&E Mr. Muhammad Zulqarnain Communication Unit Reform Support Unit Karachi | Non-availability of basic facilities; Electricity, Drinking Water, Bathrooms, Boundary Walls, Furniture & Fixture. Placement of untrained teachers/Training of teachers observed as a dire need Student Teacher Ratio (STR) was not up to standards School Administrations were not aware to SESP policy Lack of interest of community in Education Reforms
Field Observations

## Slide 11
Education & Literacy Department
Government of Sindh
JESR-II
Pictures

## Slide 12: Thanks
Education & Literacy Department
Government of Sindh
JESR-II