## Slide 1: District Planning & Implementation Sub Themes: (Implementation of SESP at District Level)
By: Syed Rasool Bux Shah
Director School Education (Secondary/Higher Secondary)
Hyderabad
27 September, 2016
Education & Literacy Department
Government of Sindh
JESR-II

## Slide 2
Disclaimer: This presentation is solely for the purpose of reference and not intended for wider dissemination and preferably to be circulated only within Local Education Group (LEG) Members and the participants of the JESR-II event. The material in this presentation has been compiled from different sources and for any further clarity, kindly contact Reform Support Unit, Education & Literacy Deptt, Govt of Sindh.

## Slide 3
Education & Literacy Department
Government of Sindh
Why District Education Plans?
After 18th Amendment and Right to Free and Compulsory Education Act (25-A), Sindh Government developed a comprehensive Sindh Education Sector Plan (SESP) 2014-18.
29 District Education Plans (DEPs) developed as roll out of Sindh Education Sector Plan (SESP).
Increased understanding of targets & activities as per SESP, inclusive of capacity building of Educational Officials.
Avoid duplication of interventions and overlap of resources.
Develop road map to align SDG-4 with DEPs.
District Situation Analysis and identification of gaps.
Improved Student Learning Outcomes.
Streamlining Development Partners’ interventions.
JESR-II

## Slide 4: Field Observations
Name of Districts | District Group Members | Observation
Nausharo Feroze Tando Allahyar | Mr. Riaz Ahmed Agro (National Commission for Human Development) Mr. Avais Inayat Memon (Management & Development Center) Mr. Mujeeb-ur-Rehman (Reform Support Unit E&LD) | DEGs meetings not held regularly. Lack of awareness regarding District Education Plan. Unavailability of DEP copies with DEG members and implementers. DEP activities funds were not allocated No follow-up to develop PC 1, for DEPs activates, due to Shortage of DDOs in district. No access to public private partnership. Lack of participation of private Sector and relevant stakeholders in the DEG meetings ECE class established though Public private partnership but no access mechanism for ED officials. Teacher not imparted (other then NTS recruited teachers) SNE according DEPs allocation are not approved. Data Center established but not functional due to unavailability of Human resource / IT Professional.
Education & Literacy Department
Government of Sindh
JESR-II

## Slide 5: Pictures

## Slide 6
Education & Literacy Department
Government of Sindh
Formation of 29 District Education Groups (DEGs) (Sept-Dec-2014).
Sensitization, orientation and capacity building of 870 DEG members on SESP (Dec-2014 to Jan-2015).
Notification and endorsement of 29 DEGs by E&LD. (Mar-2015).
Development of fully costed 29 District Education Plans (DEPs). based on situational analysis (Apr-Aug-2015).
Comprehensive review/validation of data and cost analysis of 29 DEPs (Sept-Dec-2015).
29 DEPs endorsed by respective DEGs (Aug-Dec 2015).
29 DEPs translated in Urdu & Sindhi languages (Jan-May 2016).
29 DEPs under printing in English, Urdu and Sindhi languages.
Key Achievements
JESR-II

## Slide 7
Education & Literacy Department
Government of Sindh
Objective | Activities | Target 2015-16 | Achievements | Challenges (if any)
Improved Access | Transform Kachi Classes into ECE Classes | 2,431 | 2 ECE Classes operated by Public sector 300 ECE Classes operated by Public Private Partnership | Un-availability of qualified ECE Teachers Lack of Infrastructure /Construction Resource centers were not developed due to non-establishment of ECE unit in E&LD Non-utilization of one Time Grant (OTG)
 | Establish ECE Resource Center | 33 | 2 (Khi & SBA) | 
 | Recruit ECE Teachers | 2,464 | 859 ECE teachers post reflected in FY 16-17 | 
Improved Quality of Education | Develop a Child Learning Friendly School environment | 2,431 | 302 Schools | 
 | Train teachers on assessment based on ECE curriculum | - | ECE curriculum/ standards are in review process | 
More Effective Management | Develop a database of participation in continuous professional development | - | Online ECE enrollment data base is in process | 
 | Developed HR-MIS and online Progress | - |  | 
Achievements: As per Census 2014-2015 PPP-ITA database |  |  |  | 
Early Childhood Education
JESR-II

## Slide 8
Education & Literacy Department
Government of Sindh
Objective | Activities | Target 2015-16 | Achievements | Challenges (if any)
Improved Access | Increase enrollment | 18% Primary 16% Elem | 7% Primary 3% Elem | PC-1 were not prepared due to unavailability of DDOs Lack of awareness of District Education Plans (DEPs) due to frequent transfers, posting and implementation of management cadre Shortage of IT Professional and permanent staff
 | Upgrade schools with insufficient classrooms | 1,022 | - | 
 | Construct Additional Classrooms with Basic Facility | 5,169 | - | 
 | Open Viable Schools | 1,808 | 456 | 
 | Public Private Partnership | Need base | 3,400 (Primary) | 
Improved Quality of Education | Training of Teachers on Quality Education | 22% | 17% | 
 | Capacity Building and Training of SMC | 39,447 | 21,540 (Funds Released) | 
More Effective Management | Establish Enrollment Tracking system | - | 29 Data centers established and partially functional | 
 | Develop a database of participation in continuous professional development. | - |  | 
Achievements: As per Census 2014-2015 PPP-NCHD Database New NTS Recruited Teachers (TPM) SMC Database 2014-15 |  |  |  | 
Primary & Elementary Education
JESR-II

## Slide 9
Education & Literacy Department
Government of Sindh
Objective | Activities | Target 2015-16 | Achievements | Challenges (if any)
Improved Access | Increase Enrollment | 12% | 4% | Low transition system due to no student tracking mechanism. Lack of Infrastructure /Construction Shortage of IT Professional and permanent staff
 | Rationalization of Teachers | As per need | As per SNE | 
Improved Quality of Education | Training of Teachers on Career Counselling | As per need | Under process | 
 | Training of Teachers on Quality Education | 21% | 9% | 
More Effective Management | Develop Teachers/ HR Data base | - | 29 Data centers established and partially functional | 
Achievements: As per Census 2014-2015 New NTS Recruited Teachers (TPM) |  |  |  | 
Secondary & High Secondary Education
JESR-II

## Slide 10
Education & Literacy Department
Government of Sindh
Objective | Activities | Target 2015-16 | Achievements | Challenges (if any)
Improved Access | Establish NFE Center | 485 | PC-1 for 100 Adult Literacy Centers & 50 Non Formal Education approved for following districts: Hyderabad Jamshoro Thatta Mirpurkhas Tando Allahyar Developed 1st Draft NFE’s Policy NFE Curriculum Approved | Lack of Human Resource and un-availability of Teachers at Local level. Syllabus in Process for ALC & NFE Centers.
 | Establish ALC /ALP Center for Adult | 343 |  | 
Improved Quality of Education | Training of Teachers on Teaching Techniques | 20% |  | 
 | Develop & integrate Skill Center | - |  | 
 | Mainstream of Students | - |  | 
More Effective Management | Data collection for illiterate population (13-39 age group) | - |  | 
 | HR & Database of Graduate literate candidates | - |  | 
Achievements: Directorate of NFE |  |  |  | 
Non Formal Education
JESR-II

## Slide 11: Thanks
Education & Literacy Department
Government of Sindh
JESR-II