## Slide 1: Recommendations for Governance Sub Themes: (HRMIS, M&E, Biometrics, Communication Strengthening, School Consolidation)
By: Mr. Akram Khowaja
Director General Monitoring & Evaluation- E&LD
Education & Literacy Department
Government of Sindh
JESR-II

## Slide 2: Disclaimer: This presentation is solely for the purpose of reference and not intended for wider dissemination and preferably to be circulated only within Local Education Group (LEG) Members and the participants of the JESR-II event. The material in this presentation has been compiled from different sources and for any further clarity, kindly contact Reform Support Unit, Education & Literacy Deptt, Govt of Sindh.
Education & Literacy Department
Government of Sindh
JESR-II

## Slide 3
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Challenges | Recommendations | Timelines
1. | Develop Sindh Education Policy | First time after 18th Amendment | Finalization of Concept Paper Task Force comprising dedicated professionals from public and private sector should be notified with ToRs Participation of all stakeholders Work Plan should be prepared Formation of Working Group Dedicated personnel should be identified and appointed through transfer, offered good incentives and offices and other material resources to work as the Secretariat | 6 months
SESP JESR II : Governance & Accountability

## Slide 4
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Challenges | Recommendations | Timelines
 | Introduce and establish a robust, independent, Monitoring & Evaluation System at E&LD | Budget (salary and non-salary) approval for the remaining 14 districts of Sindh; Staff recruitment and establishing M&E offices in the remaining 14 districts. Opposition from Teaching and non-teaching Staff | M&E Strategy Paper Special Summary should be moved for approval of Chief Minister Sindh Regular Coordination Meetings with District offices etc. Academic Monitoring Training of MAs on academic side An experienced Monitoring expert should be in the team of M&E System should be launched in all 29 districts Linkages with HR SMIS should be part of M&E | 3 months
SESP JESR II : Governance & Accountability

## Slide 5
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Challenges | Recommendations | Timelines
3. | Establish Management Cadre | Supreme Court’s decision will be binding and would unfold the details of permissible aspects of education management policy implementation. | Case should be pursued regularly and urgent application should be moved for hearings Human resources should also come through the competitive exam Officers of cadre should be in the department for rest of life | No timelines can be given as the matter is prejudice.
4. | Establish Human Resources Management Information System | Since the HRMIS data is sensitive, another real challenge is to achieve high level of reliability, accuracy & authenticity. | Dedicated personnel should be placed to complete the task in hand It should linkages with M&E HR people posted should be part of HRMIS | 9 months (this may take some more time as the obj. is to achieve 100% accuracy)
SESP JESR II : Governance & Accountability

## Slide 6
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Challenges | Recommendations | Timelines
5. | Establish Internal Audit System | The process of sanctioning positions and legislation can be time consuming, however the Finance Department is making the effort. | Regular follow up with Finance Department is strongly recommended for SNE etc. Dedicated Resources in terms of human and material should be allocated urgently to complete the task | 9 months
6. | Cluster-based School Management System | Since this is a major policy reform, it would need continuous support and patronage by all concerned. | Check list of school consolidation and school clustering policy needs to be notified for monitoring and implementation Ensure effective and timely implementation Resources both men material should be ensured | 9 months
SESP JESR II: Governance & Accountability

## Slide 7
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Challenges | Recommendations | Timelines
7. | Professional Development/Capacity building of DDOs and Procuring Officials | Sustainable approach and institutional arrangements to be ensured. | Regular Training programs should be scheduled and resource persons from SPPRA and Finance Department should be requested to conduct those sessions | 9 months
8. | Better equipped Offices and Logistics | This would require additional funding / approval for purchase of vehicles. | Additional resources if not available with the department should be requested to FD but immediately all offices and logistics should be provided | 9 months
SESP JESR II : Governance & Accountability

## Slide 8
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Challenges | Recommendations | Timelines
9. | Establish New System of Performance Appraisal | Real challenge would be in the implementation of the system. | Dedicated personnel should be appointed and given all material resources to complete the tasks It should be aligned with career progression It should be different for both managers and teachers based on respective performance indicators | 9-12 months
10. | Establish Information and Communication Unit | Sustainability is key to ensuring effective communication and that the outputs / outcomes are utilized in decision making. | All reforms should be properly communicated at field level Information Resource Centre should be set up for proper documentation and dissemination of information Resource Center should issue performance report of department | ICS Pilot launch tentatively by October’16 with full launch in Feb’17.
SESP JESR II : Governance & Accountability

## Slide 9
Education & Literacy Department
Government of Sindh
JESR-II
S # | Strategic Objectives | Implementation Challenges | Recommendations | Timelines
11. | Increase effectiveness of SMCs | Delayed response from the districts. Funds Utilization / Tracking. Community involvement | Delegation of financial powers Building Capacity of SMCs Strong follow up for school improvement plan Annual Conference of SMC Chairmen at district level District Administration should be made responsible for utilization of SMC Funds | 9 months
12. | Establish R&D Unit | Appropriate personnel for placement Budget allocation in the CFY as no appropriation is there | Training Programs should be started immediately and appropriate personnel should be appointed Budget allocation should be ensured in CFY Creating linkages with Academic Institutions both public and private institutions | 6 months
SESP JESR II : Governance & Accountability

## Slide 10: Thanks
Education & Literacy Department
Government of Sindh
JESR-II